## 2017
Plan of Operation |  |  | ACTION PLAN OF OPERATION Physical Year 2017
(IT section: Quality with better and faster service are ensured)
|  |  | January | February | March | April | May | June | July | August | September | October | November | December | Notes
Activities
1 | Planning and work flow and system requirements of Inventory Control System for FMCL | Plan | [12 empty] | Successfully planned along with Management & Mr. Oishi, Project cordinator
Achivement
Remarks
2 | Calling consultant for development of Online Inventory system | Plan | [12 empty] | Discussed with CEO of Chiliquest for development of Database as per our need
Achivement
Remarks
3 | Preparation of Documents to migrate from old system to new online system | Plan | [12 empty] | All different source of items are marged in to one to avoid duplication and submitted to developer for migration
Achivement
Remarks
4 | Net work Server 2008 setting to share file, printers and Internet | Plan | [12 empty] | The server 2008 was purchsed with help of project SFaMP-II projet and successfully set up is done
Achivement
Remarks
5 | Repair and maintenance system through online for easy access and transparent reporting system instantly from every region and service centers. | Plan | [12 empty] | Developer freely supported the development of repair and maintenance part & development under process
Achivement
Remarks
6 | Developing Static Website for FMCL to advetise FMCL products | Plan | [12 empty] | Developed and all information of regions and product information and slso new recruitment annouancement are done through this and
Achivement
Remarks
7 | Create Facebook, Youtube to advertise FMCL Products | Plan | [12 empty] | Created and done
Achivement
Remarks
8 | Plan and procurement of 2017 spare parts and Farm Machineries | Plan | [12 empty] | Procurement done through Tender, direct and from local
Achivement
Remarks
9 | Ad-HOC works | Plan | [12 empty] | Repair and Maintenance of Computers,laptops, Printers and net work
Achivement
Remarks
10 | Assist in Developing Procurement Guide Book | Plan
Achivement
Remarks

## 2018
Plan of Operation |  |  | ACTION PLAN OF OPERATION Physical Year 2018
(IT section: Quality with better and faster service are ensured)
|  |  | January | February | March | April | May | June | July | August | September | October | November | December | Notes
Activities
1 | Activation of Online Inventory Control System-database | Plan | [12 empty] | Activited with effect from 1st Jan, 2018
Achivement
Remarks
2 | Planning for Human Resource database system to maintain staff information | Plan | [12 empty] | Developed and activited
Achivement
Remarks
3 | Planning and developemtn of commercial website for FMCL | Plan | [12 empty] | Developed and activited cost suported by Mr. Feroz, and developer will provide fee support here after
Achivement
Remarks
4 | Planning and development of Geog apps for geog power tiller | Plan | [12 empty] | Developed and implementation is also done
Achivement
Remarks
5 | Repair and maintenance system through online for easy access and transparent reporting system instantly from every region and service centers. | Plan | [12 empty] | Developed and implementation is also done
Achivement
Remarks
6 | Managing to provide necessary services to staffs by repairing their computers, internet, network printers and designing works (calendars, leveling etc.) | Plan | [12 empty] | 6 printers connections and tested, Desigined calander for year 2018
Achivement
|  | Remarks | 7 laptops OS installation Done 9 Places internet connectiosn done(BAJO, KHANGMA, Paro, Samteling, Marketing, production,POL office and Thinley store
7 | Tendering,Procurement of farm machines and spare patrs from Japan, Thailand, India and from local | Plan | [12 empty] | Procured throughout the year base on regionals requisition and demand base
Achivement
Remarks
8 | Managing online database, Facebook youtube and ad-hoc works | Plan
Achivement
Remarks
9 | Ad-HOC works | Plan
Achivement
Remarks

## 2019
Plan of Operation |  |  | ACTION PLAN OF OPERATION Physical Year 2019
(IT section: Quality with better and faster service are ensured)
|  |  | January | February | March | April | May | June | July | August | September | October | November | December | Notes
Activities
1 | Managing online Inventory Control System database of all regions and central store | Plan | [12 empty] | * Item history incuded * Sales amount annuly and monthly bar chart is included acknowledgement is included
Achivement
Remarks
2 | Managing Human Resource database system | Plan | [12 empty] | Salary pay roll included
Achivement
Remarks
3 | Managing FMCL official website on advertising, news update and other related and product information’s are published | Plan | [12 empty] | Publishing daily bases
Achivement
Remarks
4 | Managing central hiring and geog apps made accessible though mobile and easy reporting from every part of regions | Plan | [12 empty] | re design required, make accessable to farmers to avail the service
Achivement
Remarks
5 | Managing Sales and service database (for repair and maintenance) | Plan | [12 empty] | Soomthly Functioning
Achivement
Remarks
6 | Managing to provide necessary services to staffs by repairing their computers, internet, network printers and designing works (calendars, leveling etc.) | Plan
Achivement
Remarks
7 | Data base for fix assets-Administration | Plan
Achivement
Remarks
8 | App- redevelopment making avilabe to farmers | Plan
Achivement
Remarks
9 | Database for budgeting online for accounts section | Plan
Achivement
Remarks
10 | IWP, Notesheet and TADA- online for HR | Plan
Achivement
Remarks
11 | Marketing products like rice, seseime oil ect. To bring online | Plan
Achivement
Remarks
12 | Training incountry / ex-country | Plan
Achivement
Remarks